## Study 2 Timeline
Tasks | Task ID | Task Description | 2026 | [11 empty] | 2027
Chapter 2 Study
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Task 1: Qualitative Study | B1 | Ethics/Admin & Recruitment (COMP/INFO) | bar: Jan to Dec
| B2 | 20 Semi-Structured Interviews | bar: Jan to Dec
| B3 | Transcription & Thematic Analysis | bar: Jan to Dec
Task 2: Write-up & Survey Design | B4 | Thesis Writing: Interview Results (Thesis Ch. 4) | bar: Jan to Dec
| B5 | Operationalizing Themes into Survey Items | bar: Jan to Dec
| B6 | Pilot Study (N=30) & Reliability Check | bar: Jan to Dec
Task 3: Publication Preparation #1 | B7 | Conference Paper Writing 1 (Qualitative Findings) | bar: Jan to Dec
| B8 | Submission to Conference/Journal | Jan: Milestone 1
Task 4: Quantitative Study | B9 | Full Survey Launch (N=300) & Data Audit | bar: Jan to Dec
| B10 | Construct Validity (CFA) & Stat Analysis | bar: Jan to Jul; Sep to Dec
Task 5: Synthesis & Pub Prep #2 | B11 | Thesis Writing: Cross-study Synthesis & "Discussion" Chapter | bar: Jan to Dec
| B12 | Conference Paper Wriing 2 (Quantitative/Mixed-Methods) | bar: Oct to Nov
| B12 | Submission to Conference/Journal | Jan: Milestone 2
Chapter 1 Study
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Task 1: Improving IF | A1 | Literature Review for latest implementation | bar: Jan to Jun; Aug to Dec
| A2 | Begin Experiments on IF | bar: Jan to Jul; Oct to Dec
Task 2: Write Up and Pub Prep #3 | A3 | Thesis Writing: IF Experiments | bar: Apr
| A4 | Conference Paper Writing 3 | bar: Apr to May
Task 3: Comparing Response Pair | A5 | Generate Response Pair from IF vs Non-IF enhanced | bar: Apr
| A7 | Create annotation medium | bar: Apr
| A8 | Source students annotators (N = 15) & Collect results | bar: Apr to Jun
Task 4: Selecting LLM Judge for Guidance | A9 | Run experiments of comparing human response vs AI judge | bar: Jul
| A10 | Thesis Writing: Response Pair Generation & LLM Judge | bar: Aug to Sep
| A11 | Conference Paper Writing 4 | bar: Aug to Sep
Task 5: Evaluating IF enhacement on Guidance | A9 | Run experiments with automatic annotation & Bradley Model | bar: Aug
| A10 | Thesis Writing: Task 4 and 5 results & "Discussion" Chapter | bar: Sep to Oct
Task 6: Final WriteUp and Thesis Submission | A11 | Conference Paper Writing 5 | bar: Oct to Nov
| A12 | Thesis Writeup & Submission | bar: Oct to Dec